## Sheet1
C | Inspection Date | Due Date Count | Asset I.D | System | Sub-System | Reliability Observation | Criticality | Reliability Status | End User Status | Closed Date | Reliability Confirmed Closed Date | Remarks
1 | 2025-09-24 | 196 | QC 04 | M-ROOM | in the control ystem | HMI not showing on QC04 | MEDIUM | CLOSED | CLOSED | 2025-12-11 | 2025-12-11 | OK
2 | 2025-08-23 | 228 | RTG 01 | Cabin | wiper | cabin glass wiper defective | MEDIUM | OPEN
3 | 2025-08-23 | 228 | RTG 07 | Cabin | Electrical socket not working | Cabin ( all the socket in the cabin notfunctioning | HIGH | CLOSED | CLOSED | 2025-12-26 | 2025-12-27 | OK
4 | 2025-07-29 | 253 | QC 05 | TLS tank | Cartenary | 1.Hydraulic oil shortage in QC05 TLS tank | LOW | CLOSED | CLOSED | 2026-01-09 | 2026-01-09 | OK
5 | 2025-07-29 | 253 | QC 01 | 2- Pylon Light​ | (the apex of the A-frame)​ | QC01 2- Pylon Light are defective. at the tip of the main boom or (at the apex of the A-frame)​ | HIGH | CLOSED | CLOSED | 2026-01-23 | 2026-01-23
6 | 2025-07-29 | 253 | RTG 05 | Gantry Sebre thruster brake- Main-plate | Landside gantry | Gantry Sebre thruster brake- Main-plate has proken | HIGH | CLOSED | CLOSED | 2025-12-12 | 2025-12-12 | OK
Formulas:
Due Date Count = DAYS(TODAY(),[Inspection Date])